Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product_Backlog
Product Name:	C1325 Rental Vehicle Management System					Complete Fields in Green!!!
Team ID:

Name:	Rutaben Vaghasia
Initials:	RAV
Student ID:	1001608968

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	21		Total
Sprint 1 Left	16	5	1
Sprint 2 Left	8	8	2
Sprint 3 Left	6	2	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AV	1		1	Finished in Sprint 1	Rental Agent	Add a vehicle	I can keep track of our fleet of rental vehicles
LV	2		1	Finished in Sprint 1	Rental Agent	List all vehicles	I can find out what is in the vehicle fleet	This will also be needed for the next two features
RV	3		1	Finished in Sprint 1	Rental Agent	Rent a vehicle	I can track who has rented each vehicle	Each vehicle will need to know if it is already rented or not
RT	4		1	Finished in Sprint 1	Rental Agent	Return a vehicle	I can tell when a vehicle is returned
HE	5		1	Finished in Sprint 1	Rental Agent	Get help	I can learn how to use the system
AR	12		1		Rental Agent	Add a renter	I can conveniently keep track of all renters	This is the Bonus level
SR	13		1		Rental Agent	Select a renter when renting a vehicle	I don't have to rekey recurring renter info	This is the Bonus level
SV	17		1		Rental Agent	Save data	I can retain data between program runs	This is the Extreme Bonus level
LD	18		1		Rental Agent	Load data	I can restore data on a new program run	This is the Extreme Bonus level
	6		2	Finished in Sprint 2	Developer	Copy Sprint 01 Backlog tab to this spreadsheet	I have the history of Sprint 01 available	SPRINT 2 / Homework 7 starts here
GMM	6		2	Finished in Sprint 2	Rental Agent	Use a standard dialog for the main menu	I can interact more naturally with the system
GNV	7		2	Finished in Sprint 2	Rental Agent	Use a series of dialogs for a new vehicle	I can interact more naturally with the system
GLV	8		2	Finished in Sprint 2	Rental Agent	Use a stand dialog for the list of vehicle	I can interact more naturally with the system
GH	9		2	Finished in Sprint 2	Rental Agent	Use dialogs for all other interaction (e.g., help)	I can interact more naturally with the system
GRV	10		2	Finished in Sprint 2	Rental Agent	Use dialogs for rent and return vehicle	I can interact more naturally with the system
GPM	14		2	Finished in Sprint 2	Rental Agent	Add rich text (Pango) to the main menu (dialog)	The menu is easier to navigate	This is the Bonus level
GPH	15		2	Finished in Sprint 2	Rental Agent	Add rich text (Pango) to the help dialog	The help text is easier to understand	This is the Bonus level
GDV	19		2		Rental Agent	Use a custom dialog to create new vehicles	I can create new vehicles more quickly	This is the Extreme Bonus level
GW	11		3	Finished in Sprint 3	Rental Agent	Interact with a main window with drop-down menus	I can interact more naturally with the system	SPRINT 3 / Homework 8 starts here
GT	16		3	Finished in Sprint 3	Rental Agent	Add a toolbar to the main menu	I can more quickly access common features	This is the Bonus level
GV	20		3		Rental Agent	Add a scrolling vehicles table to main window	I can more quickly look up vehicles	This is the Extreme Bonus level
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 09		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 16
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	9
Day 1 Left	9	0
Day 2 Left	9	0
Day 3 Left	9	0
Day 4 Left	9	0
Day 5 Left	9	0
Day 6 Left	5	4
Day 7 Left	0	5

	Feature ID		Description	Status	Notes
	GMM		#include gtkmm.h and add GTKFLAGS to Makefile	Completed Day 6	You may modify this list to best fit your baseline code
	GMM		Modify main menu as Input dialog	Completed Day 6	Including a test with each constructor and method is helpful
	GNV		Replace cin for new vehicle with Input and Question dialogs	Completed Day 6
	GLV		Replace cout for list of vehicles with Message dialog	Completed Day 6
	GH		Replace cout for help text with Message dialog	Completed Day 7
	GRV		Replace cin for return vehicle with Input dialog	Completed Day 7
	GRV		Replace cin for rent vehicle with Input dialogs	Completed Day 7
	GPM		Set Pango implementation	Completed Day 7	Create your own sprint backlog items for the bonus level
	GPH		Use atleast 5 different tags	Completed Day 7	You can insert more rows using right-click → Insert Rows
	GDV				Create your own sprint backlog items for the extreme bonus level
Sprint Burn Chart
Days
Tasks

## Sprint_03_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 16		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 23
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	5
Day 1 Left	5	0
Day 2 Left	5	0
Day 3 Left	5	0
Day 4 Left	5	0
Day 5 Left	5	0
Day 6 Left	2	3
Day 7 Left	0	2

	Feature ID		Description	Status	Notes
	GW		Add Main_window class with menu creation code	Completed Day 6	You may modify this list to best fit your baseline code
	GW		Create pass-through handlers for menu items to controller.execute_cmd	Completed Day 6
	GW		Fix main() to create app and run Main_window instance	Completed Day 6
	GT		Create buttons	Completed Day 7	Create your own sprint backlog items for the bonus level
	GT		add toolbars and buttons and connect handlers to c.execute.cmd	Completed Day 7	You can insert more rows using right-click → Insert Rows
	GV				Create your own sprint backlog items for the extreme bonus level
Sprint Burn Chart
Days
Tasks